## Gantt Chart
BrightTV Case Study — Project Gantt Chart
Each bar shows the planned duration (in days) for that project phase
Phase | Start Date | Duration (days) | Start Offset (days) | End Date
Project Planning & Scoping | 2026-06-01 | 3 | 0 | 2026-06-04
Data Collection & Understanding | 2026-06-04 | 2 | 3 | 2026-06-06
Data Cleaning & SQL Processing | 2026-06-06 | 5 | 5 | 2026-06-11
Excel Analysis (Pivots & Charts) | 2026-06-11 | 4 | 10 | 2026-06-15
Power BI Dashboard Build | 2026-06-15 | 3 | 14 | 2026-06-18
Looker Studio Dashboard Build | 2026-06-15 | 3 | 14 | 2026-06-18
Databricks Dashboard Build | 2026-06-18 | 2 | 17 | 2026-06-20
Web Dashboard Build (Lovable) | 2026-06-18 | 2 | 17 | 2026-06-20
Presentation Development | 2026-06-20 | 3 | 19 | 2026-06-23
Review, QA & Final Submission | 2026-06-23 | 2 | 22 | 2026-06-25
Formulas:
End Date = [Start Date]+[Duration (days)]